## Public page, client portal
Bug ID | Module / Section | Bug Title / Summary | Severity | Priority | Environment | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Suggested Technical Fix | Status
BUG-001 | Header Navigation | Excessive whitespace between "Case Studies" and "Careers" menu links | Low | P3 | Desktop Browsers (Chrome, Edge, Safari, Firefox) | Viewport width > 1024px | 1. Open the home page. 2. Focus on the main header navigation menu. 3. Observe spacing between "Case Studies" and "Careers". | Spacing between all header menu items should be uniform and visually balanced. | Large whitespace gap isolates "Case Studies" from "Careers" in the navigation layout. | Check header CSS Flexbox container; replace unintended justify-content rules or clean up margin overrides on li/a tags. | Fixed
BUG-002 | Contact Us Page / Company Address & Footer Details | Mismatch between primary office address in main body text and footer location | High | High | Chrome (Latest), Desktop Viewport (1920x1080), Production | User is navigated to the Contact Us page. | 1. Open the Contact Us page. 2. Observe the address listed under the "Office" heading in the "Let's Start a Conversation" section. 3. Scroll down to the website footer and observe the address listed under the "OUR LOCATION" heading. | Both the main body text and the footer display identical, single-source-of-truth address information for the office location. | Main body lists "123 Innovation Street San Francisco, CA 94102", whereas the footer lists "100 Innovation Way, Suite 400 San Francisco, CA 94105". | Update `ContactDetails.tsx` (or the relevant CMS data string) to source the company address from a single shared configuration constant (e.g., `COMPANY_ADDRESS`) across both components. | Fixed
BUG-003 | Contact Us Page / Form Validation | Phone field accepts invalid digit counts and poorly formatted number sequences without validation checks | High | High | Chrome (Latest), Mobile/Desktop Viewports, Production | User is on the Contact Us page form. | 1. Focus on the "Phone" input field. 2. Type an arbitrary numeric string like "1233445565788" or "233445565788" (12–13 digits). 3. Click "Send Message" or trigger blur event. 4. Observe validation response. | Phone field enforces standard digit constraints (e.g., 10 digits for US standard or E.164 international format) and flags non-conforming digit lengths. | Phone field accepts arbitrary string lengths (e.g., 13-digit inputs like "1233445565788") without throwing a validation error. | Implement strict telephone regex/libphonenumber schema validation (e.g., Yup `.matches(/^(\+?1[-. ]?)?\(?([0-9]{3})\)?[-. ]?([0-9]{3})[-. ]?([0-9]{4})$/)`) in `ContactForm.js`. | Fixed
BUG-004 | Client Dashboard / Layout & UI | Card border outlines overlap text content inside ticket metrics cards | Medium | Medium | Chrome (Latest), Desktop Viewport, Production | User views the main metrics cards on the Client Dashboard. | 1. Navigate to the Client Dashboard. 2. Look at the "Open Tickets" summary card box. 3. Observe the spacing between the card border and the text content. | Metrics cards display clean padding and margins without bounding box borders cutting through text. | The inner bounding border cuts directly across and hugs the card text ("Open Tickets", "4", "Open or assigned"), creating visual overlap. | Adjust padding, margins, and overflow styling in the CSS/Tailwind grid container for `.dashboard-metric-card`. | Fixed
BUG-005 | Client Dashboard / Header | Header user pill displays redundant role badge and username styling | Low | Low | Chrome (Latest), Desktop Viewport, Production | User is logged into the client portal. | 1. Look at the top right header navigation bar. 2. Observe the user status badges. | The header cleanly presents the scope and user account indicator. | Header displays an awkward double-badged structure (`O CLIENT` next to `CLIENT_USER`), causing duplicate scope/role label rendering. | Refactor `HeaderUserPill` component to render the active scope badge dynamically without duplicating the username text label. | Fixed
BUG-006 | Client Dashboard / Account Summary | Redundant Account Summary module occupying prime dashboard real estate | Low | Low | Chrome (Latest), Desktop Viewport, Production | User is logged into the [Client Dashboard](https://aurexion-one.vercel.app/portal/dashboard). | 1. Log in to the client portal and navigate to the [Client Dashboard](https://aurexion-one.vercel.app/portal/dashboard). 2. Scroll down to the "ACCOUNT SUMMARY" card at the bottom. 3. Compare displayed profile metadata (Username, Role) with the header user profile menu and dedicated [User Profile](https://aurexion-one.vercel.app/portal/dashboard) page. | Dashboard surface prioritizes actionable metrics, active ticket workflows, and operational alerts over static user profile metadata. | Static profile details ("USERNAME client_user", "EMAIL client@aurexion.com", "ROLE client_user", "MEMBER SINCE Aug 14, 2026") are duplicated on the main dashboard, consuming layout space. | Deprecate or remove the `AccountSummary` component from `ClientDashboardView.tsx`, ensuring user details remain accessible exclusively via the header user menu or dedicated profile route. | Fixed
BUG-007 | Client Dashboard / UI Layout | Metrics card borders overlap and clip inner text content across summary widgets | Medium | High | Chrome (Latest), Desktop Viewport, Production | User is logged into the [Client Dashboard](https://aurexion-one.vercel.app/portal/dashboard). | 1. Navigate to the [Client Dashboard](https://aurexion-one.vercel.app/portal/dashboard). 2. Inspect the "Open Tickets" and "In Progress" summary cards. 3. Observe the positioning of card borders relative to labels and values. | Metrics cards display clear margins and internal padding so that borders frame the content cleanly without clipping text. | Card bounding borders slice directly across text labels ("Open Tickets", "Currently being worked on") and numerical metrics ("4", "0"), causing visual overlap. | Fix container padding and box-sizing in `DashboardMetricsCard.tsx` (e.g., set `padding: 1.5rem` and remove fixed width/height constraint wrappers on inner flex items). | Fixed
BUG-008 | Authentication / Login Performance | Excessive latency and slow response time during user authentication login flow | High | High | Chrome (Latest), Desktop/Mobile Viewports, Production | User is on the login page with valid credentials. | 1. Enter valid client credentials into the login form. 2. Click "Login" or submit the form. 3. Measure the network request latency to complete authentication and redirect to the dashboard. | User authenticates and redirects to the dashboard seamlessly within 1–2 seconds. | Login request experiences noticeable delay/lag (taking several seconds) before authorizing and rendering the portal view. | Audit authentication API endpoint backend execution; optimize database queries, token generation latency, or switch heavy synchronous tasks to asynchronous background processing in the authentication view controller. | Fixed
BUG-009 | Client Dashboard / Layout & UI | Metrics cards stacked vertically causing excessive screen real estate wastage and unnecessary scrolling | Medium | Medium | Chrome (Latest), Desktop Viewport (1920x1080), Production | User is logged into the client portal and viewing the main dashboard. | 1. Navigate to the Client Dashboard page. 2. Observe the layout arrangement of the 4 key metrics summary cards ("Open Tickets", "In Progress", "Awaiting Client", "Resolved"). 3. Note the vertical scrolling required to view all cards. | Metrics cards are arranged horizontally in a responsive 4-column grid (or 2x2 grid on medium viewports) to utilize horizontal space efficiently and eliminate dead space. | All metrics cards stack vertically in a single column, taking up almost the entire vertical fold height and creating significant blank space on the right side of the screen. | Update CSS layout container for `DashboardMetricsGrid` to use CSS Grid/Flexbox (`display: grid; grid-template-columns: repeat(4, 1fr); gap: 1.5rem;` on `md:` and `lg:` breakpoints). | Fixed
BUG-010 | Client Portal / Custom Service Requests | Category input field rendered as freeform text input instead of structured dropdown menu | Medium | Medium | Chrome (Latest), Desktop Viewport (1920x1080), Production | User opens the "Submit Custom Request" modal on the [Enterprise Portal Requests page](https://aurexion-one.vercel.app/portal/requests). | 1. Navigate to the [Requests page](https://aurexion-one.vercel.app/portal/requests). 2. Click on the "Submit Request" button to open the modal form. 3. Attempt to select a predefined category from the "CATEGORY" field. | Category field renders as a standard select dropdown component displaying standard choices (e.g., "Feature Enhancement", "Custom Scope Addition", "Technical Inquiry", "SLA Upgrade"). | Category field renders as a plain text input field prepopulated with default text "General Request", forcing users to manually type a category instead of selecting from a predefined list. | Replace the `<input type="text">` tag for `CATEGORY` with a select menu component (`<select>` or custom UI dropdown) initialized with standard category option values in `CustomRequestModal.tsx`. | Fixed
BUG-011 | Client Portal / Custom Service Requests | Modal footer CTA button "Submit Request" is vertically clipped and partially hidden by viewport bounds | High | High | Chrome (Latest), Desktop Viewport (1080p/Laptop), Production | User is on the [Enterprise Portal Requests page](https://aurexion-one.vercel.app/portal/requests) and clicks "Submit Request" to open the modal. | 1. Navigate to the [Requests page](https://aurexion-one.vercel.app/portal/requests). 2. Click on the "Submit Request" header button to open the "Submit Custom Request" modal dialog. 3. Inspect the bottom section of the modal dialog. | Modal container remains vertically centered within the viewport with adequate padding/margin, ensuring action buttons ("Cancel", "Submit Request") are fully visible and clickable without scrolling or clipping. | The bottom modal container overflows vertically beyond the screen height, causing the primary CTA "Submit Request" button to be visually cut off and partially hidden behind the bottom browser viewport edge. | Add `max-height: 90vh; overflow-y: auto;` to the modal content body container in `CustomRequestModal.tsx` and fix the footer container (`flex-shrink: 0`) so action buttons stay anchored inside the visible viewport area. | Fixed
BUG-012 | Client Portal / Custom Service Requests | Misaligned form input margins and inconsistent label padding within modal dialog | Low | Medium | Chrome (Latest), Desktop Viewport, Production | User opens the "Submit Custom Request" modal on the [Enterprise Portal Requests page](https://aurexion-one.vercel.app/portal/requests). | 1. Open the "Submit Custom Request" modal dialog. 2. Observe the alignment of form labels ("REQUEST TITLE", "CATEGORY", "PRIORITY") relative to input borders and modal padding. | Form field inputs and select dropdowns maintain aligned left/right margins and consistent vertical field spacing. | Form input fields have inconsistent internal text padding and top/bottom margin distribution, making input boxes appear tight against label text and unevenly spaced relative to the outer modal boundary. | Standardize vertical spacing (`gap-4` or `mb-4`) across all form group wrappers in `CustomRequestModal.tsx` and adjust placeholder/input line-height and inner padding (`py-2.5 px-3`). | Fixed
BUG-013 | Global / Footer Navigation | Footer policy links (Privacy Policy, Terms of Service, Support) are unclickable text elements | Medium | Medium | Chrome (Latest), Desktop Viewport (1920x1080), Production | User scrolls to the footer on the [Enterprise Portal Requests page](https://aurexion-one.vercel.app/portal/requests) or any portal page. | 1. Scroll down to the website footer section. 2. Hover over "Privacy Policy", "Terms of Service", or "Support". 3. Attempt to click on any of the legal or support links. | Footer legal and support items render as interactive anchor elements (`<a>` tags) with appropriate hover pointer cursors that open their respective legal/support documents. | The footer links display as plain non-clickable text spans without `href` attributes, pointer cursor cues, or active click listeners. | Wrap "Privacy Policy", "Terms of Service", and "Support" text strings in standard React Router `<Link>` or `<a href="...">` components pointing to active route paths (e.g., `/privacy`, `/terms`, `/support`). | Fixed
BUG-014 | Client Portal / Custom Service Requests | Redundant Refresh CTA creates visual clutter alongside primary action controls | Low | Low | Chrome (Latest), Desktop Viewport, Production | User is on the [Enterprise Portal Requests page](https://aurexion-one.vercel.app/portal/requests). | 1. Open the [Requests page](https://aurexion-one.vercel.app/portal/requests). 2. Observe the main actions area containing both "Refresh" and "+ Submit Request" CTA buttons. | Primary action area highlights main task completion ("Submit Request") without unnecessary UI overhead if background data synchronization is active. | Refresh button takes up primary CTA space next to "Submit Request", cluttering the top action header section. | Implement automated background polling or optimistic UI updates on request submission, and remove the explicit manual `Refresh` button component from `RequestsHeader.tsx`. | Fixed
BUG-015 | Client Portal / Custom Service Requests | Success banner notification ("Request submitted successfully!") persists indefinitely without auto-dismissal or route state reset | Medium | Medium | Chrome (Latest), Desktop Viewport, Production | User successfully submits a new custom service request via the modal dialog. | 1. Navigate to the [Requests page](https://aurexion-one.vercel.app/portal/requests). 2. Submit a new custom request. 3. Observe the green "Request submitted successfully!" banner. 4. Wait several minutes or interact with other on-page elements. | Success notification automatically auto-dismisses after a short timeout (e.g., 3–5 seconds), or clears immediately when navigating/closing the page view. | The success notification alert remains permanently sticky on the UI long after the submission action is completed. | Implement an auto-dismiss timeout (e.g., `setTimeout(() => setSuccess(false), 4000)`) or reset the submit success state flag upon user interaction/component unmount in `RequestsHeader.tsx`. | Fixed
BUG-016 | Client Dashboard / Sidebar Navigation | Sidebar navigation menu is missing module routes ("Projects", "Requests", "Documents") enabled on the dashboard | High | High | Chrome (Latest), Desktop Viewport (1920x1080), Production | User is logged into the client portal and viewing the [Client Dashboard](https://aurexion-one.vercel.app/portal/dashboard). | 1. Inspect the left sidebar navigation menu (`SYSTEM SCOPE: CLIENT`). 2. Observe the available navigation menu links. 3. Compare sidebar items ([Dashboard](https://aurexion-one.vercel.app/portal/dashboard), [Support Tickets](https://aurexion-one.vercel.app/portal/support), [User Profile](https://aurexion-one.vercel.app/portal/profile)) with enabled dashboard modules ([Projects](https://aurexion-one.vercel.app/portal/projects), [Requests](https://aurexion-one.vercel.app/portal/requests), [Documents](https://aurexion-one.vercel.app/portal/documents)). | Sidebar navigation menu includes links for all active client modules ([Projects](https://aurexion-one.vercel.app/portal/projects), [Requests](https://aurexion-one.vercel.app/portal/requests), [Documents](https://aurexion-one.vercel.app/portal/documents)) to allow seamless direct navigation from anywhere in the portal. | Sidebar menu only lists [Dashboard](https://aurexion-one.vercel.app/portal/dashboard), [Support Tickets](https://aurexion-one.vercel.app/portal/support), and [User Profile](https://aurexion-one.vercel.app/portal/profile), forcing users to return to the dashboard home page to access the other active modules. | Update the navigation items array in `Sidebar.tsx` to dynamically include menu routes for `Projects` (`/portal/projects`), `Requests` (`/portal/requests`), and `Documents` (`/portal/documents`) based on active module flags. | Fixed
BUG-017 | Global Header / Navigation | Clicking logo inside authenticated portal redirects users out to public home page instead of authenticated dashboard | Medium | Medium | Chrome (Latest), Desktop Viewport (1920x1080), Production | User is authenticated and viewing an internal portal page (e.g., [Super Admin Dashboard](https://aurexion-one.vercel.app/admin/dashboard) or Client Portal). | 1. Log in to the portal as an authenticated user. 2. Click on the "AUREXION" brand logo located in the top-left corner of the header. 3. Observe the target URL navigation. | Clicking the logo while logged in redirects the user to their active portal dashboard (e.g., `/admin/dashboard` or `/portal/dashboard`). | Clicking the logo redirects the user out of the active authenticated portal session back to the public root landing page (`/` or `index.html`). | Update the header logo target route dynamically in `Header.tsx` based on user auth state (e.g., `const logoHref = isAuthenticated ? getDashboardRouteByRole(user.role) : '/';`). | Fixed

## sales
Bug ID | Module / Section | Bug Title / Summary | Severity | Priority | Environment | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Suggested Technical Fix | status
BUG 01 | CRM Module / Leads Funnel | Leads Pipeline Desk fails to fetch data showing generic network error "No response from server" | High | High | Chrome (Latest), Desktop Viewport (1920x1080), Production | User is logged into the CRM system with `SALES_EXECUTIVE` scope. | 1. Navigate to the [Leads Funnel page](https://aurexion-one.vercel.app/crm/leads). 2. Observe the main data table content area. 3. Check network response in developer tools. | Leads Pipeline Desk fetches and renders active leads list or displays an "Empty Leads" empty state if no records exist. | The table area displays a persistent error message: `"No response from server. Please check your network connection."` even when network connection is online. | Check the API endpoint target URL in `LeadsFunnelView.js` for CORS misconfigurations, authorization header missing/expired token handling, or backend server route failures (`500/502`). | Fixed
BUG 02 | CRM / Create Sales Lead Modal | Modal dialog overlay z-index failure causes top modal header to overlap and bleed into global header | Medium | High | Chrome (Latest), Desktop Viewport (1080p), Production | User opens the "Create Sales Lead" modal on the [Leads Funnel page](https://aurexion-one.vercel.app/crm/leads). | 1. Click "+ Create Lead" button to launch the modal dialog. 2. Observe the top boundary of the modal window relative to the global navigation header (`AUREXION`). | Modal backdrop and container sit on a higher z-index layer than the fixed global header, fully obscuring the page background and preventing overlap. | The top section of the modal ("NEW CRM ENTRY") overlaps directly with the top navigation bar (`AUREXION ¦ O SALES_EXECUTIVE`), causing text bleeding and visual collision. | Increase the modal container and overlay backdrop `z-index` in `CreateLeadModal.tsx` (e.g., set `z-index: 50` or `z-index: 9999`) to ensure it renders cleanly above the global header (`z-index: 40`). | Fixed
BUG 03 | CRM / Create Sales Lead Modal | Modal backdrop z-index layering causes global header elements to bleed through the overlay | Medium | Medium | Chrome (Latest), Desktop Viewport (1080p), Production | User opens the "Create Sales Lead" modal on the [Leads Funnel page](https://aurexion-one.vercel.app/crm/leads). | 1. Click the "+ Create Lead" button. 2. Observe the top boundary of the modal dialog relative to the top navigation bar. | Modal backdrop overlay renders on top of all page elements (including the fixed global header) to focus user attention strictly on the form. | The global top header (`AUREXION ¦ O SALES_EXECUTIVE`) sits visually above the modal top header (`NEW CRM ENTRY`), allowing header text to bleed through the backdrop. | Increase the modal overlay container `z-index` in CSS (e.g., `z-index: 50`) relative to the fixed top header (`z-index: 40`) in `CreateLeadModal.tsx`. | Fixed
BUG 04 | CRM / Create Sales Lead Modal | Required field indicators lack accessible form validation styling or explicit tooltips | Low | Low | Chrome (Latest), Desktop Viewport, Production | User opens the "Create Sales Lead" modal on the [Leads Funnel page](https://aurexion-one.vercel.app/crm/leads). | 1. Inspect required fields ("CONTACT NAME *", "EMAIL ADDRESS *"). 2. Submit the form empty or hover over required asterisks. | Required fields feature clear visual validation highlights and standard accessible field tooltips indicating mandatory entry requirements. | Required field indicators rely solely on a plain text asterisk (`*`) without visual field focus styling or explicit validation message prompts. | Add standard `required` HTML attributes and dynamic error state styling (`border-red-500`) with clear inline helper text for invalid/empty submissions in `CreateLeadModal.tsx`. | Fixed
BUG 05 | CRM / Create Sales Lead Modal | Form submission fails displaying "ERROR // No response from server" due to broken endpoint or API network error | High | High | Chrome (Latest), Desktop Viewport, Production | User opens the "Create Sales Lead" modal on the [Leads Funnel page](https://aurexion-one.vercel.app/crm/leads) and fills in lead details. | 1. Click "+ Create Lead" to open the form. 2. Enter contact details ("Mubeena", "jhon@gmail.com"). 3. Click "Establish Lead" (or attempt initial fetch/submit). 4. Observe error banner inside modal. | The form successfully posts lead data to the backend API, closes the modal, and refreshes the leads list with a success notification. | Form submission or initial fetch inside the modal fails, rendering the persistent banner: `"ERROR // No response from server. Please check your network connection."` | Verify the endpoint URL and payload structure in `CreateLeadModal.tsx`; ensure proper CORS configuration, backend API route availability (`POST /api/crm/leads`), and valid user authorization headers. | Fixed

## Aurexion
Bug ID | Bug Title | Module | Description | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status
AUR-LOGIN-001 | Username and password fields are pre-filled on opening the login page | Login Page | When the login page is opened, the Admin role is automatically selected, the username field contains “administrator,” and the password field is also populated. Login credentials should not be pre-filled by the application because this may expose privileged account information and allow unauthorized access. | Open the page in Incognito/InPrivate mode with browser autofill disabled to confirm the values are supplied by the application. | Open an Incognito/InPrivate browser window. Navigate to `https://aurexion-one.vercel.app/login`. Observe the selected role. Observe the Username or Email field. Observe the Password field. | The username/email and password fields should be empty when the login page loads. No default or hardcoded administrator credentials should be displayed. | The Admin role is selected automatically, the username is pre-filled as “administrator,” and the password field contains a pre-filled masked value. | Critical — if the populated password is a valid application-provided administrator credential. Otherwise, Medium if caused only by browser autofill. | High | Fixed
AUR-LOGIN-002 | Login page displays `404 NOT_FOUND` when the user refreshes the page or navigates back | Login Page | The login page loads initially, but refreshing it or returning to it using the browser’s Back button displays a Vercel `404 NOT_FOUND` error. This prevents users from accessing the login page. | The Aurexion application is open in the browser. | Refresh: Navigate to `https://aurexion-one.vercel.app/login`. Wait for the login page to load. Refresh the browser page. Observe the result. Back button: Open the login page. Navigate to another page or proceed from the login page. Click the browser’s Back button to return to `/login`. Observe the result. | The login page should load correctly after refreshing or returning through browser navigation. | The application displays a Vercel error page containing: 404: NOT_FOUND Code: `NOT_FOUND` The login form is unavailable. | High — users cannot access the login page through normal browser navigation. | High (P1) — fix before production release. | Fixed
AUR-EST-003 | “Next” button is not working in the Homepage Project Estimator | Homepage → Estimate Your Project | After selecting a project type in Step 01 of the Project Estimator, clicking the Next button does not proceed to the next step. The estimator remains on the current screen, preventing the user from completing the project estimation process. | The Aurexion homepage is open, and the user has scrolled to the Estimate Your Project section. | Navigate to `https://aurexion-one.vercel.app`. Scroll down to Estimate Your Project. Select any project type under What are you building?, such as Digital Transformation. Click the Next button. Observe the result. | After selecting a project type and clicking Next, the estimator should proceed from Step 01 to Step 02 and display the next set of questions. | Clicking the Next button produces no response. The estimator remains on Step 01, and the user cannot continue. | High — the main functionality of the Project Estimator is blocked. | High (P1) — should be fixed before the production release. | Fixed
AUR-CMS-004 | CMS dashboard metrics fail to load after successful CMS login | CMS Portal → Dashboard | After successfully logging in as a Content Manager, the CMS portal and its other modules are accessible. However, only the CMS Dashboard fails to load its metrics and displays an error message. | A valid Content Manager account is available. The user is successfully logged into the CMS portal. | Open the Aurexion login page. Log in using valid Content Manager credentials. Navigate to CMS Control. Observe the Dashboard section. | The CMS Dashboard should display its metrics, summary counts, and related information. | Only the Dashboard metrics fail to load. The following message is displayed: Unable to load CMS Dashboard Metrics Error: Other CMS modules remain accessible. | Medium — the Dashboard is unavailable, but the remaining CMS modules can still be used. | High (P1) — the Dashboard is an important monitoring and summary feature. | Fixed
AUR-CMS-005 | Services Catalog and industries fails to load and displays an unspecified error | CMS Portal → Services Catalog | After logging in as a Content Manager and opening the Services Catalog, the service records fail to load. The page displays an error state with a Retry button, but it does not show the actual error message. | The user is logged in with valid Content Manager credentials. The CMS portal is accessible. | Log in to the CMS portal as a Content Manager. Select Services Catalog from the left navigation menu. Wait for the services to load. Observe the results section. | The Services Catalog should load and display the available service records with accurate published, draft and featured counts. | The service records do not load. The page shows: Error: Retry The error reason is blank, and all summary counts display `0`. | High — the Content Manager cannot view or manage the existing service records. | High (P1) | Fixed
AUR-ADMIN-006 | Operator Detailed Metadata popup content is not clearly visible | Admin Portal → Users → Operator Detailed Metadata | When an administrator opens an operator’s detailed metadata, the popup appears over the user table without a proper opaque background or overlay. The underlying table content remains visible and overlaps visually with the metadata, making the operator details difficult to read. | The administrator is logged into the Admin Portal. User records are available in the User Management section. | Log in to the Aurexion Admin Portal. Navigate to Users. Locate any operator in the user table. Click the View icon under Actions. Observe the Operator Detailed Metadata popup. | The metadata should appear inside a clearly visible modal with: An opaque or sufficiently contrasting background A dimmed page overlay Proper spacing and alignment Clearly readable labels and values No visual interference from the underlying table | The modal background appears transparent. Text and table content behind the popup remain visible and overlap with the operator metadata, reducing readability. | Medium — the functionality opens, but important operator information is difficult to read. | Medium (P2) | Fixed
AUR-CRM-007 | CRM Activities page fails to load and displays “No response from server” | CRM Portal → Activities, Lead Funnel, contact forms | When the CRM Portal Activities page is opened, the application fails to retrieve the activity data and displays a server/network connection error. As a result, CRM activities cannot be viewed or managed. | The CRM Portal is accessible. A valid CRM Portal session is active. The device has an active internet connection. | Log in to the CRM Portal with valid credentials. Navigate to CRM Portal → Activities. Alternatively, open `https://aurexion-one.vercel.app/crm/activities`. Wait for the activity information to load. Observe the result. | The CRM Portal Activities page should load successfully and display all available activity records. | The CRM Portal Activities page fails to retrieve the records and displays: No response from server. Please check your network connection. | High — the CRM Portal Activities functionality is unavailable. | High (P1) | Fixed
AUR-UI-008 | Footer logo is inconsistent with the Aurexion header logo | Public Website → Footer | The Aurexion branding displayed in the website footer does not match the official logo shown in the header. The header contains the Aurexion symbol and wordmark, while the footer displays only a text-based AUREXION logo with different styling and colour. | The Aurexion public website is accessible and the Estimator page loads successfully. | Navigate to `https://aurexion-one.vercel.app/estimator`. Observe the Aurexion logo in the page header. Scroll down to the footer. Compare the footer logo with the header logo. | The footer should display the approved Aurexion logo with the same: Brand symbol Wordmark Font style Colour scheme Proportions and spacing | The footer displays a text-only AUREXION logo with different typography and colour. It does not include the brand symbol shown in the header, resulting in inconsistent branding. | Low — this is a visual and branding issue that does not block functionality. | Medium (P2) — should be corrected to maintain consistent brand identity across the website. | Fixed
AUR-REC-09 | “View Resume” returns a 404 error in Candidate Pool Application Map | Recruitment Portal → Candidate Pool → Application Map | In the Candidate Pool Application Map, clicking the option to view a candidate’s resume redirects to a `404 Not Found` page. The resume is neither displayed nor downloaded, preventing the recruitment team from reviewing the candidate’s document. | The Recruitment Portal is accessible. A valid Recruitment Portal session is active. At least one candidate application with an uploaded resume is available. | Log in to the Aurexion Recruitment Portal. Navigate to `https://aurexion-one.vercel.app/recruitment/candidates`. Open Candidate Pool. Locate the Application Map. Select a candidate with an uploaded resume. Click View Resume. Observe the result. | The selected candidate’s resume should open in the browser. If browser preview is unavailable, the resume should download successfully. | Clicking View Resume displays a `404 Not Found` error. The resume is not displayed or downloaded. | Not specified | Not specified | Fixed
AUR-SUP-010 | Ticket created in Client Portal is not reflected in Support Portal | Client Portal → Support Tickets / Support Portal → Support Desk | A support ticket created successfully from the Client Portal does not appear in the Support Portal. The Support Operations Dashboard continues to show zero tickets, preventing the support team from receiving and processing the client’s request. | Valid Client Portal and Support Portal accounts are available. A support ticket can be submitted from the Client Portal. The ticket submission is confirmed as successful. | Log in to the Client Portal. Navigate to the Support Tickets section. Create a new ticket using valid information. Confirm that the ticket was submitted successfully and record its ticket ID. Log in to the Support Portal as a Support Executive. Open Support Desk. Check the dashboard and Tickets Queue. Refresh the page and observe the results. | The ticket created in the Client Portal should appear in the Support Portal’s incoming or unassigned ticket queue. After assignment, it should appear in the assigned Support Executive’s dashboard and Tickets Queue with the correct details and status. | The ticket is created in the Client Portal but is not visible in the Support Portal. The dashboard continues to display: Total Assigned: `0` Open & Assigned: `0` In Progress: `0` Recent Assigned Tickets: No ticket displayed | High — client issues may not reach the support team, causing requests to remain unattended. | High (P1) BUG-HIGH-11: Non-Dynamic Dynamic Service and Industry Page Routing (Missing Relational Database Querying): | Fixed
BUG-HIGH-011 | Non-Dynamic Service and Industry Page Routing (Missing Relational Database Querying) | Services and Industries | Service and Industry items (mandated across 32 services and 18 sectors) are rendered via static frontend lists or anchor links rather than being dynamically generated from database models with dynamic slug routes (e.g., /services/python-development/). Steps to Reproduce: 1. Navigate to the homepage or navigation bar sections for Services or Industries. 2. Click on individual service offerings or industry sector cards (e.g., "Core Engineering", "AI & Data Science"). 3. Check the address bar URL, route transitions, and underlying source response. Expected Results: Clicking a service or sector should query the relational PostgreSQL Service or Industry model and render dynamic detail pages under specific URL slugs with full SEO schema mapping per PRD Section 4.2 & 4.3. Actual Results: Controls route to generic anchor tags (e.g., #) or static frontend cards without triggering dynamic backend routing or fetching model instances. Severity: High Priority: P2 .BUG-HIGH-12C: Non-Dynamic Blog CMS & Insights Engine (Missing Backend Post Indexing): | The Aurexion public website is accessible, and the Services and Industries sections are available. | Navigate to the homepage or navigation bar sections for Services or Industries. 2. Click on individual service offerings or industry sector cards (e.g., "Core Engineering", "AI & Data Science"). 3. Check the address bar URL, route transitions, and underlying source response. Expected Results: Clicking a service or sector should query the relational PostgreSQL Service or Industry model and render dynamic detail pages under specific URL slugs with full SEO schema mapping per PRD Section 4.2 & 4.3. Actual Results: Controls route to generic anchor tags (e.g., #) or static frontend cards without triggering dynamic backend routing or fetching model instances. Severity: High Priority: P2 .BUG-HIGH-12C: Non-Dynamic Blog CMS & Insights Engine (Missing Backend Post Indexing): | Clicking a service or sector should query the relational PostgreSQL Service or Industry model and render dynamic detail pages under specific URL slugs with full SEO schema mapping per PRD Section 4.2 & 4.3. Actual Results: Controls route to generic anchor tags (e.g., #) or static frontend cards without triggering dynamic backend routing or fetching model instances. Severity: High Priority: P2 .BUG-HIGH-12C: Non-Dynamic Blog CMS & Insights Engine (Missing Backend Post Indexing): | Controls route to generic anchor tags (e.g., #) or static frontend cards without triggering dynamic backend routing or fetching model instances. Severity: High Priority: P2 .BUG-HIGH-12C: Non-Dynamic Blog CMS & Insights Engine (Missing Backend Post Indexing): | High Priority: P2 .BUG-HIGH-12C: Non-Dynamic Blog CMS & Insights Engine (Missing Backend Post Indexing): | P2 .BUG-HIGH-12C: Non-Dynamic Blog CMS & Insights Engine (Missing Backend Post Indexing): | Fixed
BUG-HIGH-12C | Non-Dynamic Blog CMS and Insights Engine (Missing Backend Post Indexing) | Insights / Blog | The Insights / Blog module is rendered as a static frontend UI with hardcoded card components, lacking a dynamic Content Management System (CMS), database-driven post indexing, tag filtering, or a backend API connection to PostgreSQL as mandated in PRD Section 4.11. Steps to Reproduce: 1. Navigate to the INSIGHTS section (/insights or /blog). 2. Attempt to filter or search posts by category, tag, or author. 3. Click on individual blog post preview cards to access full articles. 4. Inspect network activity via Developer Tools (F12 $\rightarrow$ Network $\rightarrow$ Fetch/XHR). 5. Observe that post content is served from local client-side JSON files or static frontend templates rather than executing database queries against an API route (e.g., /api/v1/blog/posts/). Expected Results: The Insights module must feature a dynamic Blog CMS connected to PostgreSQL that supports real-time post retrieval, category filtering, search querying, and dynamic URL slug routing (/insights/post-slug/) via Django REST Framework endpoints. Actual Results: The section displays only hardcoded static UI card previews. There is no dynamic backend indexing system, dynamic routing for individual post instances, or database querying. Severity: High Priority: P1 BUG-HIGH-13: Static Vercel Hosting and Missing Django/PostgreSQL Backend Execution: | The Aurexion public website is accessible, and the Insights or Blog section is available. | Navigate to the INSIGHTS section (/insights or /blog). 2. Attempt to filter or search posts by category, tag, or author. 3. Click on individual blog post preview cards to access full articles. 4. Inspect network activity via Developer Tools (F12 $\rightarrow$ Network $\rightarrow$ Fetch/XHR). 5. Observe that post content is served from local client-side JSON files or static frontend templates rather than executing database queries against an API route (e.g., /api/v1/blog/posts/). Expected Results: The Insights module must feature a dynamic Blog CMS connected to PostgreSQL that supports real-time post retrieval, category filtering, search querying, and dynamic URL slug routing (/insights/post-slug/) via Django REST Framework endpoints. Actual Results: The section displays only hardcoded static UI card previews. There is no dynamic backend indexing system, dynamic routing for individual post instances, or database querying. Severity: High Priority: P1 BUG-HIGH-13: Static Vercel Hosting and Missing Django/PostgreSQL Backend Execution: | The Insights module must feature a dynamic Blog CMS connected to PostgreSQL that supports real-time post retrieval, category filtering, search querying, and dynamic URL slug routing (/insights/post-slug/) via Django REST Framework endpoints. Actual Results: The section displays only hardcoded static UI card previews. There is no dynamic backend indexing system, dynamic routing for individual post instances, or database querying. Severity: High Priority: P1 BUG-HIGH-13: Static Vercel Hosting and Missing Django/PostgreSQL Backend Execution: | The section displays only hardcoded static UI card previews. There is no dynamic backend indexing system, dynamic routing for individual post instances, or database querying. Severity: High Priority: P1 BUG-HIGH-13: Static Vercel Hosting and Missing Django/PostgreSQL Backend Execution: | High Priority: P1 BUG-HIGH-13: Static Vercel Hosting and Missing Django/PostgreSQL Backend Execution: | P1 BUG-HIGH-13: Static Vercel Hosting and Missing Django/PostgreSQL Backend Execution: | Fixed
BUG-HIGH-01 | Static Vercel Hosting and Missing Django/PostgreSQL Backend Execution | Backend Infrastructure and Deployment | The live deployment operates exclusively as a static frontend hosted on Vercel without a Python 3.11+, Django REST Framework (DRF), or PostgreSQL backend infrastructure to handle dynamic routing, business logic, or data storage. Steps to Reproduce: 1. Open [https://aurexion-one.vercel.app/](https://aurexion-one.vercel.app/) in a web browser. 2. Inspect network traffic via Developer Tools (F12) -> Network tab. 3. Navigate through the application and trigger functional controls. 4. Observe that all network requests serve static HTML, CSS, JS, or hardcoded JSON assets, with zero WSGI/ASGI API transactions routed to a Python server or PostgreSQL database. Expected Results: The application must be backed by a running Python 3.11+ Django/DRF service connected to a PostgreSQL database as specified in PRD Section 3.1 & 13.2. Actual Results: The application is hosted as a purely static frontend site on Vercel (aurexion-one.vercel.app) with no active Django backend or PostgreSQL layer. Severity: Critical Priority: P1 (Highest) BUG-HIGH-014: Missing Enterprise Lead Management System (Mini-CRM) and Admin Control Center: | The deployed Aurexion application is accessible in a browser, and Developer Tools are available for inspecting network requests. | Open [https://aurexion-one.vercel.app/](https://aurexion-one.vercel.app/) in a web browser. 2. Inspect network traffic via Developer Tools (F12) -> Network tab. 3. Navigate through the application and trigger functional controls. 4. Observe that all network requests serve static HTML, CSS, JS, or hardcoded JSON assets, with zero WSGI/ASGI API transactions routed to a Python server or PostgreSQL database. Expected Results: The application must be backed by a running Python 3.11+ Django/DRF service connected to a PostgreSQL database as specified in PRD Section 3.1 & 13.2. Actual Results: The application is hosted as a purely static frontend site on Vercel (aurexion-one.vercel.app) with no active Django backend or PostgreSQL layer. Severity: Critical Priority: P1 (Highest) BUG-HIGH-014: Missing Enterprise Lead Management System (Mini-CRM) and Admin Control Center: | The application must be backed by a running Python 3.11+ Django/DRF service connected to a PostgreSQL database as specified in PRD Section 3.1 & 13.2. Actual Results: The application is hosted as a purely static frontend site on Vercel (aurexion-one.vercel.app) with no active Django backend or PostgreSQL layer. Severity: Critical Priority: P1 (Highest) BUG-HIGH-014: Missing Enterprise Lead Management System (Mini-CRM) and Admin Control Center: | The application is hosted as a purely static frontend site on Vercel (aurexion-one.vercel.app) with no active Django backend or PostgreSQL layer. Severity: Critical Priority: P1 (Highest) BUG-HIGH-014: Missing Enterprise Lead Management System (Mini-CRM) and Admin Control Center: | Critical Priority: P1 (Highest) BUG-HIGH-014: Missing Enterprise Lead Management System (Mini-CRM) and Admin Control Center: | P1 (Highest) BUG-HIGH-014: Missing Enterprise Lead Management System (Mini-CRM) and Admin Control Center: | Fixed
BUG-HIGH-014 | Missing Enterprise Lead Management System (Mini-CRM) and Admin Control Center | Admin Control Center / Mini-CRM | The system lacks an authenticated Admin Control Center and Lead Management System (Mini-CRM) with Role-Based Access Control (RBAC), KPI metric visualizers, state machine transition controls (NEW → WON/LOST), and system audit logging. Steps to Reproduce: 1. Click on LOGIN or navigate toward the administrative access routes (e.g., /admin or /dashboard). 2. Attempt to authenticate using admin or business development management (BDM) credentials. 3. Observe available routes and accessible administrative tools. Expected Results: Authorized users (BDM/Admin) should log in through an authenticated gateway and access an Admin Control Center with KPI metrics, lead state-machine handlers, and audit log viewers per PRD Section 4.7 & 5.1. Actual Results: No functional RBAC login, administrative control center, lead state machine, or audit tracking interface is accessible or implemented. Severity: High Priority: P1 | The Aurexion application is accessible, and the administrative login routes can be opened. | Click on LOGIN or navigate toward the administrative access routes (e.g., /admin or /dashboard). 2. Attempt to authenticate using admin or business development management (BDM) credentials. 3. Observe available routes and accessible administrative tools. Expected Results: Authorized users (BDM/Admin) should log in through an authenticated gateway and access an Admin Control Center with KPI metrics, lead state-machine handlers, and audit log viewers per PRD Section 4.7 & 5.1. Actual Results: No functional RBAC login, administrative control center, lead state machine, or audit tracking interface is accessible or implemented. Severity: High Priority: P1 | Authorized users (BDM/Admin) should log in through an authenticated gateway and access an Admin Control Center with KPI metrics, lead state-machine handlers, and audit log viewers per PRD Section 4.7 & 5.1. Actual Results: No functional RBAC login, administrative control center, lead state machine, or audit tracking interface is accessible or implemented. Severity: High Priority: P1 | No functional RBAC login, administrative control center, lead state machine, or audit tracking interface is accessible or implemented. Severity: High Priority: P1 | High Priority: P1 | P1 | Fixed
AUR-CLIENT-015 | Required Client Portal navigation menu items are missing | Client Portal → Navigation Menu | Essential Client Portal navigation options are missing | Client is logged in to the Client Portal. | 1. Log in as Client. 2. Open the Client Portal. 3. Check the navigation menu. | The menu should display Dashboard, My Projects, Project Tracker, Document Vault, Support Tickets, Consultation Schedule, Notifications, Profile and Logout. | Only Dashboard, Support Tickets and User Profile are displayed. |  |  | Fixed
AUR-CRM-016 | Complete RFP and Contact Form details are not clearly displayed in Leads Funnel | CRM → Leads Funnel | Complete information submitted through RFP and Contact Forms is not displayed. | A valid form has been submitted, and the Sales Executive is logged in. | 1. Submit an RFP or Contact Form. 2. Log in to CRM. 3. Open Leads Funnel. 4. Open the corresponding lead. | All submitted details and attachments should be stored and displayed in the lead record. | Only limited lead information is displayed. Complete form details are missing or unclear. | High | High | Fixed
AUR-CRM-017 | Unable to open lead details from Leads Funnel | CRM → Leads Funnel → Lead Details | The selected lead details fail to load. | Sales Executive is logged in, and at least one lead is available. | 1. Open CRM. 2. Go to Leads Funnel. 3. Select a lead. 4. Click Open Desk. | The Lead Details page should display complete customer, project and activity information. | The page displays “Lead Record Unavailable” and “No response from server.” | High | High | Fixed
AUR-CRM-018 | CRM Dashboard takes more than 10 seconds to load or displays a server error | CRM Portal → CRM Dashboard | The dashboard loads slowly or fails to load. | Sales Executive is logged in to the CRM Portal. | 1. Log in. 2. Open CRM Dashboard. 3. Measure the loading time. 4. Refresh and repeat the test. | The dashboard should load database-driven metrics within the required response time without server errors. | The dashboard takes more than 10 seconds to load or displays a server error. | High | High | Fixed
AUR-CMS-019 | CMS Dashboard fails to load because the Services API returns 404 | CMS Portal → CMS Control Dashboard | The CMS Dashboard cannot load metrics because the Services API fails. | Content Manager is logged in to the CMS Portal. | 1. Log in. 2. Open CMS Control. 3. Check the dashboard. 4. Inspect Network requests. | The CMS API should return a successful response and display accurate CMS metrics. | The dashboard displays “Unable to load CMS Dashboard Metrics,” and the Services API returns 404. | High | High | Fixed
AUR-CMS-020 | Industries Directory fails to load because the Industries API returns 404 | CMS Portal → Industries | The Industries Directory cannot display industry records. | Content Manager is logged in to the CMS Portal. | 1. Log in. 2. Open CMS → Industries. 3. Check the directory. 4. Inspect the API request. | The page should load industry records and allow authorized content management. | The page displays “Error: Request failed,” “0 Domains Mapped,” and the API returns 404. | High | High | Fixed
AUR-BDM-021 | Submitted RFPs are not displayed in the BDM Portal | BDM Portal → RFP Engine | Successfully submitted RFP forms do not appear in the RFP Engine. | At least one valid RFP has been submitted, and the BDM user is logged in. | 1. Submit an RFP. 2. Log in to the BDM Portal. 3. Open RFP Engine. 4. Check the submissions. | Every RFP should be stored, assigned an AUR-RFP ID, displayed in the RFP Engine and linked to a lead. | The RFP Engine displays “0 Total RFPs” and “No RFP submissions found.” | High | High | Fixed
AUR-BDM-022 | Cost Estimator displays predefined values without user interaction | BDM Portal → Cost Estimator | The estimator automatically displays input values before user interaction. | BDM user has opened the Cost Estimator without entering data. | 1. Open Cost Estimator. 2. Check the Headcount and Project Timeline fields. | Fields should be empty or identified as default values. Calculations should start only after user confirmation. | Headcount and timeline are automatically populated with 5 and 6. | Medium | Medium | Fixed
AUR-HR-023 | Recruitment Desk unable to load HR Dashboard metrics | Recruitment → Recruitment Desk | The HR dashboard metrics fail to load due to an authentication error. | User is logged in with the HR Manager role. | 1. Log in as HR Manager. 2. Open Recruitment Desk. 3. Observe the dashboard. | The authenticated HR Manager should see the recruitment dashboard metrics. | The system displays “Authentication credentials were not provided.” | High | High | Fixed
AUR-HR-024 | Job Openings Board fails to load vacancies | Recruitment → Jobs Board | The Jobs Board does not display vacancies due to an authentication error. | User is logged in with the HR Manager role. | 1. Log in as HR Manager. 2. Open Jobs Board. 3. Observe the vacancies. | The authenticated HR Manager should see all available job vacancies. | The system displays “Authentication credentials were not provided.” | High | High | Fixed
AUR-HR-025 | Candidate Pool and Application Map fail to load | Recruitment → Candidate Pool/Application Map | Candidate and application data fail to load due to an authentication error. | User is logged in with the HR Manager role. | 1. Log in. 2. Open Candidate Pool. 3. Open Application Map. 4. Observe the data. | The authenticated HR Manager should see candidate and application records. | The system displays “Authentication credentials were not provided.” | High | High | Fixed
AUR-ADMIN-026 | Admin Support tickets fail to load due to expired session | Admin Portal → Support Management | Support tickets cannot be accessed because API requests return 401. | User is logged in with the Admin role. | 1. Log in to the Admin Portal. 2. Open Support. 3. Observe the Support Management Console. | A valid Admin session should load all support tickets. An expired session should redirect the user to login. | The system displays a session-expired message, and API requests return 401 Unauthorized. | Critical | High | Fixed
AUR-ADMIN-027 | User deactivation occurs without a confirmation popup | Admin Portal → User Management | An operator is deactivated without confirmation. | Admin is logged in, and an active operator is available. | 1. Open User Management. 2. Select an active operator. 3. Click Deactivate. | A confirmation popup should appear before deactivation. | The operator is deactivated immediately without confirmation. | High | High | Fixed
AUR-ADMIN-028 | Authenticated Admin session returns 401 for all Admin APIs | Admin Control Center → Authentication/API Integration | Protected Admin APIs fail despite an active Admin login. | User is logged in with Admin access. | 1. Log in. 2. Open Admin Settings. 3. Inspect API requests in the Network tab. | Admin API requests should include a valid token and return successful responses. | Users, roles, leads, tickets, projects and other APIs return 401 Unauthorized. | Critical | P0 – Immediate | Fixed
AUR-LOGIN-029 | Valid Client login redirects to the public landing page | Authentication → Client Login | A successfully authenticated Client is redirected to the wrong page. | A valid and active Client account exists. | 1. Open Login. 2. Select the Client role. 3. Enter valid credentials. 4. Click Login. | The Client should be redirected to the Client Portal dashboard. | The Client is redirected to the public landing page. | Critical | P0 – Immediate | Fixed
AUR-BDM-030 | Open Full Workspace fails to fetch workspace data | BDM → Lead Details | The selected lead’s full workspace does not open. | BDM user is logged in, and an RFP lead is available. | 1. Log in to the BDM Portal. 2. Open an RFP lead. 3. Click Open Full Workspace. | The workspace should open and display complete lead information. | The workspace does not open and displays “Failed to fetch.” | High | High | Fixed
AUR-BDM-031 | Open Full Workspace fails to fetch workspace data | BDM → Lead Details | The selected lead’s full workspace does not open. | BDM user is logged in, and an RFP lead is available. | 1. Log in to the BDM Portal. 2. Open an RFP lead. 3. Click Open Full Workspace. | The workspace should open and display complete lead information. | The workspace does not open and displays “Failed to fetch.” | High | High | Fixed
AUR-CONTACT-032 | Contact Form submission returns 500 Internal Server Error | Public Website → Contact Us | The contact form fails to submit because the server returns a 500 Internal Server Error. | The Contact Us page is accessible, and valid information is available for all mandatory fields. | 1. Open the Contact Us page. 2. Enter valid details in all mandatory fields. 3. Click Submit/Send Message. | The form should submit successfully, store the enquiry in the database-backed Lead CRM, and display a confirmation message. | The form returns a 500 Internal Server Error, and the enquiry is not submitted. | High | High | Fixed
AUR-RFP-033 | RFP form submission fails due to request timeout | Public Website → Submit RFP | The RFP form submission fails because the request times out after approximately 15 seconds. | The Submit RFP page is accessible, and valid information is available for all mandatory fields. | 1. Open the Submit RFP page. 2. Enter valid information in all mandatory fields. 3. Click Submit. | The RFP should be saved successfully, generate an AUR-RFP-YYYY-XXXXX reference number, send confirmation to the client, and create a corresponding lead record. | The request is cancelled after approximately 15 seconds and displays “Request timed out. Please check your connection and try again.” | High | High | Fixed
AUR-ABOUT-034 | About page does not initiate a request to retrieve dynamic page content | Public Website → About Us | No observable API request retrieves dynamic About-page content. | The About Us page is accessible, and browser Developer Tools are available. | 1. Open the About Us page. 2. Open Developer Tools and select Network. 3. Refresh the page. 4. Review the network requests. | The About page should display company information dynamically populated from the PostgreSQL database. | Only an external Unsplash image request is observed. No API request for About-page information is visible. | High | High | Fixed
AUR-SALES-035 | Decline button does not update contact form lead status | Sales CRM → Contact Forms | Clicking Decline does not update the status of the selected contact form lead. | A Sales CRM user is logged in, and at least one contact form submission is available. | 1. Log in to Sales CRM. 2. Navigate to Contact Forms. 3. Click Decline for a contact form submission. 4. Check the lead status. | The lead should be declined, and its status should update accordingly. | The lead status does not change after clicking Decline. | High | High | Fixed